## ProjectTaskList
Week | Task | Priority | Status | Notes | Due Date | DONE
Week 1 | Set up project structure (React + Vite frontend & backend) | High | Completed |  | Day 1 | 1
Week 1 | Configure Tailwind CSS setup | High | Ongoing |  | Day 1 | 0
Week 1 | Create Navbar component in React | Medium | Ongoing |  | Day 2 | 0
Week 1 | Create Footer component in React | Medium | Ongoing |  | Day 2 | 0
Week 1 | Build Home Page in React (hero section, toggle feature) | High | Ongoing |  | Day 3-4 | 0
Week 1 | Build Our Story page | Medium | Ongoing |  | Day 4 | 0
Week 1 | Create Auth Page layout | Medium | Ongoing |  | Day 5 | 0
0
Week 2 | Develop Programs page | High | Pending |  | Day 1-2 | 0
Week 2 | Develop Learning Paths page | High | Pending |  | Day 2-3 | 0
Week 2 | Build FAQs with accordion style | Medium | Pending |  | Day 3 | 0
Week 2 | Build Contact Us page (form + map) | Medium | Pending |  | Day 4 | 0
Week 2 | Build Register page | High | Pending |  | Day 4 | 0
Week 2 | Implement responsive design for all pages | Medium | Pending |  | Day 5 | 0
Week 2 | Test cross-page navigation | Low | Pending |  | Day 5 | 0
Week 3 | Build Dashboard template (static) | High | Pending |  | Day 1 | 0
Week 3 | Setup Flask backend folder structure | High | Pending |  | Day 1 | 0
Week 3 | Configure Firebase project | High | Pending |  | Day 2 | 0
Week 3 | Setup Firebase integration | High | Pending |  | Day 2-3 | 0
Week 3 | Add animations & JavaScript interactivity | Medium | Pending |  | Day 3-4 | 0
Week 3 | Create Flask app configuration | High | Pending |  | Day 4 | 0
Week 3 | Setup database models | Medium | Pending |  | Day 5 | 0
Week 4 | Implement Firebase authentication | High | Pending |  | Day 1-2 | 0
Week 4 | Connect forms to Firebase | High | Pending |  | Day 2-3 | 0
Week 4 | Build API endpoints | High | Pending |  | Day 3 | 0
Week 4 | Insert images, icons, and assets | Medium | Pending |  | Day 4 | 0
Week 4 | Test user registration flow | High | Pending |  | Day 4 | 0
Week 4 | Test user authentication flow | High | Pending |  | Day 5 | 0
Week 4 | Implement error handling | Medium | Pending |  | Day 5 | 0
Week 5 | Cross-browser testing (Chrome, Firefox, Safari) | High | Pending |  | Day 1 | 0
Week 5 | Mobile responsiveness testing | High | Pending |  | Day 1 | 0
Week 5 | Fix UI/UX bugs | High | Pending |  | Day 2 | 0
Week 5 | Performance optimization | Medium | Pending |  | Day 3 | 0
Week 5 | Final testing & quality assurance | High | Pending |  | Day 3-4 | 0
Week 5 | Create project documentation | Medium | Pending |  | Day 4 | 0
Week 5 | Prepare deployment configuration | High | Pending |  | Day 5 | 0
Week 5 | Final project delivery | High | Pending |  | Day 5 | 0

## Help
HELP
https://www.vertex42.com/ExcelTemplates/task-list-template.html |  | © 2017-2019 Vertex42 LLC
About
This task list template provides a simple way to list and track your tasks. It also includes columns for budget and hours. You can delete or add columns and rows as needed. This worksheet was kept simple intentionally. If you would a more advanced way to create a task list for a project, try a Gantt Chart.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
Learn more about Drop-Down Lists
Conditional Formatting
The Priority, % Complete, and Done columns use conditional formatting in different ways. If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
The Done column is updated automatically. When you enter 100% in the % Complete column, the checkmark should appear in the Done column. You can use the drop-down in the Done column if you prefer.
Learn more about Conditional Formatting
Subtotals in the Budget Column
The Total Budget amount uses the SUBTOTAL(9,sum_range) function, that will ignore other SUBTOTAL functions contained within the sum_range.
If you want to create subtotals for each project, you can use the SUBTOTAL(9,sum_range) function.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.

## ©
Project Task List Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/task-list-template.html
© 2017-2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet